## ARCHER Core Features
ARCHER FEATURES AND FUNCTIONALITY - COMPREHENSIVE EDITION | Unnamed: 1 | Unnamed: 2 | Unnamed: 3
FEATURE NAME | DESCRIPTION | TECHNICAL REQUIREMENTS / IMPLEMENTATION | STATUS
CORE VOICE INTERACTION & COMMUNICATION
Voice Launch | The program is launched using a verbal command. ARCHER should have active listening at all times monitoring to hear the wake word. | PC should have active listening at all times monitoring to hear the wake word. Wake word detection using models like Porcupine or openWakeWord. | IN PROGRESS
Voice Authentication | Program will only respond to my voice unless permission granted for another user. Program requires an authentication parameter that will only respond to my command and will also allow permission to another person to use temporarily if I provide permission. | Speaker identification using voice biometrics. Implement voice embedding models (e.g., x-vectors, ECAPA-TDNN) for speaker verification. Session-based temporary access with automatic reset after 10 seconds of silence. | IN PROGRESS
Text-to-Speech (TTS) | A state of the art TTS model is a primary feature of the program. Low latency needed for conversational flow. | Currently using Chatterbox TTS with emotional control. Consider alternatives: Kokoro TTS (highly rated), StyleTTS2, or ParlerTTS for natural speech. GPU acceleration required. Emotional modulation capabilities essential. | COMPLETE
Speech-to-Text (STT) | User is able to interface with program using STT. Low latency needed. | Using Faster Whisper with GPU acceleration. Alternative: Whisper large-v3 for better accuracy. Real-time streaming transcription preferred. | IN PROGRESS
Filler Audio | The Orchestrator should immediately signal the TTS engine to play a pre-selected "pondering" audio file as soon as it receives a query it knows will take >1 second to process. | Library of humanlike filler sounds: "Hmm", "Let me see", "One moment", etc. Context-aware selection based on query type. Immediate playback while processing. | PLANNED
Streaming Responses | To minimize latency, the LLM should stream its text response token-by-token directly to the TTS engine, which then generates and plays audio in real-time. | Token-level streaming from LLM to TTS. Chunk-based TTS synthesis with overlap to avoid gaps. Real-time audio playback pipeline. | IN PROGRESS
Interruption (Barge-In) | The user must be able to interrupt ARCHER while it is speaking, causing it to stop and listen. | Voice Activity Detection (VAD) (e.g., silero-vad) running continuously. Immediate TTS playback kill on VAD trigger. State management to track conversation context. Resume capability if interruption was just clarification. | PLANNED
Voice Cloning | Ability to clone and use custom voices for TTS, allowing personalization or character voices. | Use StyleTTS2 or YourTTS for voice cloning from 10-30 second audio samples. Store voice embeddings for different personas. GPU required for real-time synthesis. | FUTURE
Emotion Detection in Voice | Detect user emotional state from voice characteristics (tone, pitch, speed, etc.). | Implement audio emotion recognition using models like wav2vec2-emotion or custom LSTM/transformer models. Features: pitch, energy, spectral characteristics. Integration with Therapist Agent for behavioral profiling. | FUTURE
Multi-Language Support | Support for multiple languages in both STT and TTS with automatic language detection. | Whisper for multilingual STT (supports 99+ languages). TTS models with multilingual support (e.g., VITS multilingual). Auto language detection from audio input. | FUTURE
USER INTERFACE & VISUALIZATION
Desktop GUI | Windows desktop for written prompts, responses, webcam feed, and voice visualizer orb. | 4 quadrant console widgets: canvas, orb, webcam, and input. Must also have dropdown menu to select canvas theme, TTS model adjustments, and other features. Built with PyQt6. | IN PROGRESS
Orb Visualization | Animated orb that provides visual feedback on ARCHER state (listening, thinking, speaking, idle). | Real-time animation synced with voice states. Particle effects, color changes, breathing animations. Integration with audio levels for speech visualization. | IN PROGRESS
Webcam Feed | Live camera feed in GUI for computer vision features. | Network camera integration via Blue Iris for multi-camera support with two-way audio. RTSP stream integration into PyQt6. Fallback to USB webcam. | IN PROGRESS
Canvas Widget | Customizable display area for visualizations, charts, images, and other outputs. | Themeable canvas with support for: charts/graphs, image display, document preview, web content rendering, custom visualizations. | IN PROGRESS
Augmented Reality Overlay | AR overlay capability showing information about objects ARCHER sees through webcam. | Use computer vision for object detection. Overlay identified objects with labels, information, or contextual data. Integration with knowledge graphs for object information retrieval. | FUTURE
3D Avatar | Optional 3D animated avatar that can lip-sync with TTS and show expressions. | Use Ready Player Me or custom 3D model. Lip-sync using phoneme extraction from TTS. Expression mapping from conversation context. Renders in Canvas widget. | FUTURE
Multi-Monitor Support | Ability to span ARCHER interface across multiple monitors or have different widgets on different screens. | PyQt6 multi-screen detection and positioning. Save/restore window layouts. Drag widgets between monitors. | PLANNED
INTELLIGENCE & ORCHESTRATION
Multiple Agents | Program utilizes multiple task-dedicated agents that work together. | Specialized agents: Therapist, Trainer, Financial Expert, R&D, Assistant, Observer. Agent coordination and communication protocols. | IN PROGRESS
Orchestrator | Program utilizes a primary "Orchestrator" agent that receives all inputs, decides which agent should handle the task, queries memory for context, and routes the final response. | LangGraph Master Control Program (MCP) acting as central brain. Agentic framework for function-calling/tool-using. Message queue (RabbitMQ/ZeroMQ) for inter-agent communication. DeepSeek R1 model for reasoning. | IN PROGRESS
Quality Gate / Verification | Second LLM instance that reviews primary responses for accuracy, safety, and hallucination detection. | Separate verification model that checks factual accuracy. Cross-reference with memory and knowledge base. Confidence scoring system. Flag uncertain responses for web search verification. | PLANNED
Context Management | Sophisticated management of conversation context with summarization for long conversations. | Sliding window context with summarization. Key fact extraction and storage. Context compression techniques. Retrieve relevant context from memory for each interaction. | IN PROGRESS
Reasoning Chain Visualization | Display ARCHER reasoning process visually, showing how it arrived at conclusions. | Integrate with DeepSeek R1 chain-of-thought reasoning. Display reasoning steps in Canvas. Transparency in decision-making process. | PLANNED
Multi-Agent Collaboration | Agents can consult with each other and work together on complex tasks. | Inter-agent messaging protocol. Shared memory access. Task delegation and coordination. Example: Financial Agent consults R&D Agent for AI stock analysis. | FUTURE
Self-Reflection & Learning | ARCHER reviews its own performance and learns from mistakes. | End-of-day reflection process analyzing success/failure of responses. User feedback incorporation. Automated improvement suggestions. Pattern recognition in errors. | FUTURE
MEMORY SYSTEM
Quad-Core Memory System | Comprehensive memory system for context, recall, and learning. | Short-Term: LLM context window. Long-Term (Profile): ChromaDB for facts/preferences. Episodic (Events): SQLite for timestamped events. Semantic (Knowledge): Vector DB or knowledge graph (Neo4j). | IN PROGRESS
Memory Consolidation | After each interaction, summarize conversation and store relevant information. | Memory agent summarizes conversations. Facts embedded and stored in vector DB. Events logged with timestamps. Automatic nightly consolidation and deduplication. | IN PROGRESS
Memory Retrieval | The Orchestrator queries memory databases before every interaction to build context-aware prompts. | Hybrid search (semantic + keyword). Relevance ranking. Time-based weighting (recent more important). Context-specific retrieval based on query type. | IN PROGRESS
Memory Graphs | Knowledge graph representation of relationships between entities in memory. | Neo4j graph database for entity relationships. Automatic entity extraction and linking. Temporal relationships. Example: "Mom -> called_about -> vacation_plans" with timestamp. | FUTURE
Forgetting Mechanism | Ability to gracefully forget unimportant or outdated information. | Decay function for old memories. User-directed forgetting. Privacy-preserving automatic purge of sensitive data. Importance scoring for memory retention. | FUTURE
Memory Export/Import | Backup and restore memory system, transfer to new devices. | Encrypted backup of all databases. Version-controlled memory snapshots. Migration tools for hardware upgrades. Privacy-preserving anonymized backups. | PLANNED
ENVIRONMENTAL INTERACTION & AWARENESS
Passive Observation | ARCHER constantly monitors webcam and mic feeds to build rich profile of user and environment. | OpenCV for webcam access. Local multi-modal vision model (Llava, Fuyu-8B, or similar). VAD for ambient audio. Capture frame every 5-10 seconds with vision model description. Privacy-first: all processing local, 10TB storage for logs. | PLANNED
Computer Vision Analysis | Interpret camera frames to understand user state and environment. | Scene understanding: "User at desk, looks focused". Object detection: identify food, people, objects. Activity recognition: sitting, standing, exercising. Facial expression analysis for emotional state. | PLANNED
Pose Estimation & Form Analysis | Track body pose and joint positions for exercise form correction and health monitoring. | MediaPipe Pose or OpenPose for 33-point body tracking. Real-time posture analysis with 2D/3D pose estimation. Integration with Trainer Agent for workout guidance. Fall detection for safety. Ergonomics analysis for desk work. | PLANNED
Gesture Recognition | Recognize hand gestures and body movements for touchless control. | MediaPipe Hands for hand tracking. Custom gesture library. Air-drawing capabilities. Volume control, window switching via gestures. Emergency gestures for critical commands. | FUTURE
Eye Tracking & Gaze Detection | Track where user is looking for attention-aware interactions. | Pupil detection and gaze estimation. Attention monitoring for presentations. Reading speed analysis. Fatigue detection from eye movement patterns. Screen time tracking. | FUTURE
Object Recognition & Tracking | Identify and track objects in environment for context-aware assistance. | YOLO11 for real-time object detection. Track commonly used items. Reminder system: "You left your keys on the desk". Inventory tracking for home items. | FUTURE
Activity Recognition | Understand what user is doing based on visual and audio cues. | Classify activities: working, exercising, cooking, relaxing, sleeping. Multi-modal fusion (vision + audio + time). Automatic context switching based on activity. Privacy modes for sensitive activities. | FUTURE
Face Recognition | Identify people in environment for security and social context. | Face detection and recognition for family/friends. Visitor identification and logging. Integration with calendar for meeting prep. Privacy controls for recognition data. | FUTURE
COMPUTER CONTROL & AUTOMATION
Computer Control | ARCHER can directly control the host PC with verbal failsafe. | OS automation (pyautogui for mouse/keyboard, subprocess for commands). Computer agent with defined functions. High-priority "HALT" command for emergency stop. Confirmation required for destructive operations. | HIGH PRIORITY
Remote Access | Access ARCHER core functions via smartphone when away from home. | Secure web API (FastAPI). Web-based frontend (React or Streamlit). JWT authentication. Self-hosted reverse proxy or VPN. Voice recording upload for remote commands. Audio response download. | PLANNED
Window Management | Advanced window manipulation, virtual desktop switching, workspace management. | Multi-monitor window arrangement. Save/restore workspace layouts. Auto-organize windows by task. Virtual desktop switching. Application-specific positioning rules. | HIGH PRIORITY
Macro Recording & Playback | Record sequences of actions and replay them on command. | Record mouse/keyboard sequences. Variable insertion for dynamic macros. Scheduled macro execution. Voice-triggered complex workflows. Example: "Start morning routine" (opens apps, websites, files). | FUTURE
Smart Home Integration | Control smart home devices via Home Assistant or direct APIs. | Home Assistant integration via MCP server. Control lights, thermostats, locks, cameras. Scenes and automation triggers. Voice commands for home control. Integration with passive observation for automation. | HIGH PRIORITY
File Management | Advanced file operations, organization, and search capabilities. | Natural language file search currently implemented. Future: Auto-organization by project/topic. Duplicate detection. Cloud sync status monitoring. File tagging and metadata. | IN PROGRESS
PROACTIVE AGENTS & SPECIALIZED INTELLIGENCE
Assistant Agent | Manages day-to-day tasks: reminders, email/text monitoring, local search. | APIs for Google (Calendar, Gmail), Twilio (SMS). Web scraping for local events. Email summarization and priority alerts. Calendar management. Reminder system (COMPLETE). | PLANNED
Therapist Agent | Monitors habits/behaviors, defines personality, provides emotional intelligence and proactive check-ins. | Fine-tuned LLM for personality/EI. Analyzes observation/memory data for patterns. Generates proactive check-ins at appropriate times. Provides real-time emotional context to Orchestrator. NOT scheduled check-ins, but natural friend-like observations. | PLANNED
Trainer Agent | Monitors nutrition and activity, prompts for exercise and dietary course correction. | Vision model identifies food for nutrition logging. Database of nutrition facts and exercises. Timer for sedentary alerts. Medication/vitamin tracking. Builds daily routine adaptable to energy level. Persistent encouragement. Integration with pose estimation for form correction. | PLANNED
Financial Expert Agent | Stays current on financial markets, provides data and proactive advice. | APIs: yfinance, Alpha Vantage, Polygon.io. LLM fine-tuned for financial analysis. Portfolio tracking and monitoring. High-volatility alerts. Earnings call notifications. Technical and fundamental analysis. CLEAR disclaimer: not licensed financial advice. | PLANNED
R&D Self-Improvement Agent | Actively monitors AI innovations to find adaptable technologies for ARCHER improvement. | Web scraping (BeautifulSoup, Scrapy). Research agent with summarization LLM. Sources: ArXiv, Hugging Face, GitHub, AI blogs. Scheduled daily/weekly scans. Generates "Suggested Upgrades" report. Keywords: TTS models, LLM optimization, agentic architecture, GPU improvements. | PLANNED
Learning & Education Agent | Helps user learn new skills and increase neuroplasticity with structured lesson plans and progress tracking. | Curriculum generation based on learning goals. Spaced repetition scheduling. Quiz generation and knowledge assessment. Resource recommendations (videos, articles, courses). Progress tracking and achievement system. | FUTURE
Productivity Coach Agent | Analyzes work patterns and provides productivity improvement suggestions. | Time tracking by application and activity. Distraction detection and alerts. Focus session management (Pomodoro). Productivity analytics and reporting. Workload balancing recommendations. Integration with calendar for optimal task scheduling. | FUTURE
Social Relationship Manager | Tracks relationships and helps maintain social connections. | Contact relationship mapping. Communication frequency tracking. Birthday/anniversary reminders. Suggested check-in times. Gift idea generation based on interests. Meeting prep with person-specific context. | FUTURE
Creative Collaboration Agent | Assists with brainstorming, writing, coding, and creative projects. | Multi-modal ideation support (text, image, code). Project context maintenance. Version tracking for creative work. Style consistency checking. Research assistance. Collaboration with other agents for specialized input. | FUTURE
Security & Privacy Agent | Monitors for security threats and manages privacy settings. | Suspicious activity detection. Password health monitoring. Privacy audit of outgoing data. Encryption status verification. Security update recommendations. Anomaly detection in system behavior. | FUTURE
ADVANCED & EXPERIMENTAL FEATURES
Real-Time Visual Q&A | Answer questions about what ARCHER sees through the camera. | Multi-modal vision-language model (LLaVA, GPT-4V equivalent). "What am I holding?", "Read this document", "Describe what you see". Real-time video stream analysis. | HIGH PRIORITY
Screen Content Understanding | ARCHER can see and understand what on your screen to provide context-aware help. | Screen capture integration. OCR for text extraction. Layout understanding. Application context awareness. "Summarize this page", "Find the error in this code", "What this email about?". | HIGH PRIORITY
Document Analysis & Extraction | Extract information from documents, forms, receipts via camera or upload. | OCR with layout preservation. Form field extraction. Receipt parsing for expense tracking. Document classification. Integration with memory for document retrieval. | FUTURE
Real-Time Translation | Translate text, speech, or visual text (signs, menus) in real-time. | Camera-based text detection and translation. Speech translation with voice output. Subtitle generation for videos. Multi-language conversation facilitation. | FUTURE
Predictive Assistance | Anticipate user needs based on patterns and provide suggestions before being asked. | Pattern recognition in daily routines. Context-aware suggestions. Weather-based clothing recommendations. Traffic-based departure time alerts. Proactive information retrieval based on calendar. | FUTURE
Event Triggers & Automation | Set up complex conditional automations based on multiple triggers. | If-this-then-that rules engine. Multi-condition triggers. Time-based automations. Environment-based automations. Example: "If I wake up before 6am on weekdays, suggest coffee and show market pre-open data". | FUTURE
Conversational Memory Search | Natural language search through past conversations and observations. | Semantic search across all interactions. Time-range filtering. Context reconstruction. "What did we discuss about X last month?", "When did I last mention Y?". Currently implemented via conversation_search tool. | IN PROGRESS
MCP Server Integration | Connect to external services via Model Context Protocol servers. | Home Assistant MCP for smart home. Slack/Discord MCP for messaging. Google Drive MCP for documents. Custom MCP servers for proprietary systems. Extensible architecture for new integrations. | PLANNED
API Ecosystem | Comprehensive API for third-party integrations and custom tools. | RESTful API for all ARCHER functions. WebSocket for real-time communication. OAuth for secure third-party access. Rate limiting and authentication. SDK for common languages. | FUTURE
Mobile Companion App | Full-featured mobile app for iOS/Android with voice, text, and camera input. | Native apps with push notifications. Voice command support. Camera integration for visual queries. Location-aware features. Sync with desktop ARCHER. Background listening (privacy-controlled). | FUTURE
Wearable Integration | Connect with smartwatches, fitness trackers, AR glasses. | Health data sync from Apple Watch, Fitbit, etc. Quick voice commands from watch. AR glasses for visual overlay. Haptic feedback for notifications. Biometric data integration. | FUTURE
Drone Control | Control and coordinate drone for aerial surveillance and delivery tasks. | Based on previous drone control specifications discussed. Android phone as flight computer. Real-time coordination with ARCHER. Autonomous flight paths. Camera feed analysis. Task-based missions. | FUTURE
Personal Analytics Dashboard | Comprehensive dashboard showing insights about productivity, health, habits, finances. | Time-series visualizations. Correlation analysis (e.g., sleep vs productivity). Goal tracking with progress metrics. Comparative analytics (week-over-week, month-over-month). Exportable reports. | FUTURE
Life Logging & Journaling | Automated life logging with manual journal entries and AI-assisted reflection. | Automatic daily summaries. Photo/video attachment to entries. Mood tracking over time. AI-generated reflections and insights. Searchable journal with semantic search. Encryption for privacy. | FUTURE
Voice Biomarkers for Health | Detect health indicators from voice characteristics. | Stress level detection. Fatigue analysis. Early illness detection (cold, flu). Mental health indicators (depression, anxiety markers). Trend analysis over time. DISCLAIMER: not medical diagnosis. | FUTURE
Privacy Modes | Configurable privacy levels for different contexts and data types. | Pause observation mode. Selective memory retention. Incognito conversations (no storage). Data type controls (voice, video, location). Time-based auto-delete rules. | HIGH PRIORITY
Local-Only Processing | Ensure all sensitive processing stays on local hardware. | No cloud dependencies for core functions. Local LLM models. Local STT/TTS. Local vision models. Optional cloud features clearly labeled and consent-based. | IN PROGRESS
Data Encryption | Encrypt all stored data and communications. | AES-256 encryption for databases. TLS for all network communication. Encrypted backups. Password manager integration for credentials. Biometric unlock options. | PLANNED
Audit Logs | Comprehensive logging of all ARCHER actions for transparency. | Immutable audit trail. User access logs. Agent decision logs. External API calls. Privacy-preserving log retention. Searchable audit interface. | PLANNED
Accessibility Features | Ensure ARCHER is usable by people with disabilities. | Screen reader compatibility. High contrast themes. Voice-only mode (no screen required). Gesture alternatives for voice commands. Adjustable speech rate and voice. Subtitles for TTS output. | FUTURE
Customizable Interaction Style | Adjust ARCHER personality, verbosity, and interaction patterns. | Personality presets (professional, casual, humorous). Verbosity control (brief vs detailed). Proactivity level adjustment. Notification frequency. Formality level. Cultural adaptation. | FUTURE
STATUS LEGEND
COMPLETE | Feature is fully implemented and working
IN PROGRESS | Feature is currently being developed
PLANNED | Feature is planned for near-term implementation
HIGH PRIORITY | NEW - High priority feature for next development phase
FUTURE | NEW - Future enhancement, lower priority

## Project Plan
Module / Vibe Agent | Key Responsibilities | Integration Notes
Voice Interaction Agent | Implement wake-word/voice launch, voice authentication, and integrate multi-language STT & TTS engines. Add filler audio and streaming responses, handle barge-in and voice cloning, detect emotions and support multi-language speech. | Expose unified API endpoints for STT/TTS streaming; share authentication tokens with orchestrator; provide event hooks for barge‑in and emotion updates; support pluggable voice providers.
UI & Visualization Agent | Develop desktop and cross‑platform GUI, including orb visualisation, webcam feed display, canvas widgets, augmented reality overlay, 3D avatar and multi‑monitor layouts. | Consume status/events from orchestrator and memory; render responses and agent status; provide UI controls for user input (keyboard/mouse/voice).
Orchestration & Memory Agent | Build orchestrator for coordinating multiple agents, implement quality gates and context management, visualise reasoning chains, enable multi‑agent collaboration and self‑reflection. Implement the memory system with consolidation, retrieval, graph structures, forgetting, and export/import capabilities. | Acts as central hub; communicates via message bus; stores persistent state; provides context snapshots to sub‑agents; ensures memory privacy and encryption.
Environmental Interaction Agent | Implement passive observation and computer vision capabilities such as pose estimation, gesture and activity recognition, object tracking, eye‑gaze detection and face recognition. | Provide real‑time data streams to orchestrator; trigger context updates based on observed events; optional integration with 3D avatar for mirroring user motions.
Automation & System Control Agent | Implement computer control and automation functions: remote desktop, window management, macro recording/playback, smart home integration, file management and event triggers. | Expose APIs for orchestrator to execute system commands; ensure secure remote access; integrate with smart home hubs via standard protocols.
Proactive & Specialized Agents | Develop specialized sub‑agents (assistant, therapist, trainer, financial expert, R&D agent, learning & education, productivity coach, social relationship manager, creative collaborator, security/privacy agent). Each sub‑agent encodes domain knowledge and interacts through orchestrator. | Register each sub‑agent with orchestrator; ensure access controls and personalization; share memory and context via the central hub.
Advanced & Experimental Features Agent | Implement advanced capabilities: real‑time visual Q&A, screen content understanding, document extraction, real‑time translation, predictive assistance, conversational memory search, personal analytics dashboard, life logging, voice biomarkers, privacy modes and local‑only processing. Include MCP server and API ecosystem integration, mobile/wearable/drone companions. | Integrate with orchestrator via plugin system; ensure cross‑device synchronization; respect privacy and offline settings; provide event triggers and automation scripts.
Enhancements & New Features Agent | Implement new enhancements: tool integration & workflow automation; knowledge base ingestion and RAG; natural conversation (endpoint detection, noise management, backchanneling); call transcription and analysis; agent squads and flow blocks with multi‑LLM support; telephony, cross‑device sync and offline mode; emotional & multi‑party interactions; privacy controls & human oversight; real‑time cross‑language translation with voice cloning. | Work closely with all other agents; provide connectors for external tools and telephony APIs; handle privacy configuration; share analytics and transcription with memory; integrate voice translation pipeline into Voice Interaction Agent.

## Dev Agents Plan
Agent Name | Role/Scope | Initial Prompt | Integration Approach | Communication & Coordination
Voice Pipeline Developer | Implement complete voice pipeline including wake word detection, voice authentication, speech-to-text (STT) and text-to-speech (TTS) with multi-language support, filler audio, streaming responses, barge-in handling, voice cloning and emotion detection. | You are an AI coding assistant responsible for the voice pipeline of ARCHER.Implement modules for wake word detection (using openWakeWord), voice authentication (using speechbrain/pyannote), multi-language STT (Faster-Whisper with CUDA) and TTS (F5-TTS).Support streaming responses, filler audio cues, barge‑in interruption, voice cloning and emotion detection.Use the existing `src/voice` directory as your workspace, follow Windows audio conventions, and write unit tests.Provide clear functions (e.g., `listen_and_transcribe()`, `authenticate_voice()`, `synthesize_speech()`) and document their APIs for integration. | Expose high-level functions (e.g., start_listening, stop_listening, transcribe) and events for wake word and authentication.Return transcribed text and emotion metadata to the orchestrator; accept synthesized text from orchestrator for TTS playback.Use asynchronous callbacks or message queues to avoid blocking other modules. | Commit your code to the `voice-pipeline` branch. Provide progress updates to the project manager.Flag dependencies on new models or hardware. Participate in integration testing when orchestrator signals readiness.
UI & Visualization Developer | Develop cross‑platform user interfaces: desktop GUI, orb visualizations, webcam feed overlay, canvas widgets, augmented reality views, 3D avatar and multi‑monitor support. | You are an AI coding assistant responsible for ARCHER’s user interface.Implement a Windows desktop GUI and a web/Gradio interface located in `src/ui`.Render the voice pipeline’s output (transcribed text and responses), embed orb animations and face avatar, display live webcam feeds, and build canvases for additional widgets.Plan for future AR overlays and multi‑monitor layouts.Ensure accessibility and theming support and follow the repo’s coding standards. | Interact with the orchestrator via WebSocket or API to receive messages and update the UI in real time.Provide user input events back to the orchestrator.Use modular components so the orchestrator can enable/disable UI widgets. | Work on a `ui` branch. Coordinate with the voice and orchestrator developers for data formats.Schedule UI integration tests after the orchestrator exposes endpoints.Report any issues with rendering performance or accessibility.
Orchestration & Memory Developer | Implement central orchestrator for routing tasks between agents, handle quality gates, context management, reasoning chain visualization, multi‑agent collaboration and self‑reflection. Build the memory system (short‑term, long‑term, episodic, semantic). | You are an AI coding assistant responsible for the orchestrator and memory system.Design and implement a central coordinator (`src/agents/orchestrator.py`) that receives events from the voice pipeline and UI, routes requests to specialized agents, and maintains conversation context.Implement quality gate verification, context management and reasoning chain visualization.Develop memory modules in `src/memory` (short‑term, long‑term vector stores, episodic logs, semantic graphs) and connect them to the orchestrator.Provide APIs for storing and retrieving memories, consolidating experiences and exporting/importing memory snapshots. | Expose REST or message bus endpoints for other modules to send and receive tasks.Use a shared context object and assign conversation IDs to coordinate state.Register specialized agents at startup; orchestrator invokes them and tracks their responses.Persist memories asynchronously to avoid blocking.Document the orchestrator API for other developers. | Develop on the `orchestrator` branch. Communicate required data structures to all other developers.Schedule integration sessions when voice, UI and specialized agents are ready.Keep track of performance and optimize for concurrency.
Environmental Interaction Developer | Implement environmental perception: passive observation, computer vision analysis (pose estimation, gesture and activity recognition), eye‑tracking & gaze detection, object tracking and face recognition. | You are an AI coding assistant responsible for ARCHER’s environmental perception.Develop modules in `src/vision` to capture and process webcam streams using OpenCV or other vision libraries.Implement pose estimation, gesture recognition, activity classification, gaze tracking, object and face recognition.Integrate with the voice pipeline for synchronized audio‑visual cues and send events (e.g., user looking away) to the orchestrator. | Provide event hooks and continuous streams of detected activities to the orchestrator via asynchronous callbacks.Expose an API to enable or disable specific vision modules based on privacy settings.Synchronize timestamps with the voice pipeline for multimodal understanding. | Work in the `vision` branch. Coordinate with the orchestrator developer to define event schemas.Flag hardware dependencies (e.g., GPU). Ensure privacy and user consent settings are respected.
Automation & System Control Developer | Implement computer control, remote access, window management, macro recording/playback, smart home integration and file management. | You are an AI coding assistant responsible for automation and system control.Develop modules in `src/automation` that can control Windows OS functions: simulate keyboard/mouse input, manage windows, record/playback macros, access remote machines, integrate smart home devices via APIs, and manage files.Ensure all actions respect security policies and user confirmation. | Expose a high-level command API for the orchestrator (e.g., `execute_command(command_name, params)`).Use event-driven architecture to report success/failure back to the orchestrator.Implement permission checks and auditing to meet privacy and security requirements. | Develop on the `automation` branch. Coordinate with security/privacy developer to align on permission models.Schedule integration tests with the orchestrator when ready.
Proactive & Specialized Agents Developer | Develop specialized sub‑agents: assistant, therapist, trainer, financial expert, R&D agent, learning coach, productivity coach, social relationship manager, creative collaborator and security/privacy agent. | You are an AI coding assistant responsible for specialized agents in ARCHER.Implement agent classes in `src/agents` for each domain (assistant, therapist, trainer, stock_expert, authority_manager, federated_learning, governance, etc.).Each agent should define its capabilities, tools, and knowledge sources.Implement method(s) for the orchestrator to call them and for agents to provide responses with tool invocations if needed.Design prompts and tasks specific to each domain, using the latest research and compliance guidelines. | Agents register themselves with the orchestrator at startup.They receive tasks via the orchestrator, perform domain‑specific reasoning and tool calls, and return results.Implement optional caching or summarization to reduce latency.Ensure agents follow rules defined in config/agents.yaml. | Develop on the `specialized-agents` branch. Collaborate with the orchestrator developer to define agent registration and API protocols.Ensure each agent meets privacy and ethical guidelines.Participate in human-in-the-loop testing with the user to refine agent behaviour.
Advanced & Experimental Features Developer | Develop advanced features: real‑time visual Q&A, screen content understanding, document analysis & extraction, predictive assistance, event triggers & automation, conversational memory search, MCP server integration, API ecosystem, mobile/wearable/drone clients, analytics dashboard, life logging, voice biomarkers for health, privacy modes and local‑only processing. | You are an AI coding assistant responsible for advanced and experimental features in ARCHER.Implement modules to process screen captures for Q&A and content understanding, parse documents, build predictive assistance, implement event triggers and automation scripts, design memory search algorithms and personal analytics dashboards.Integrate with MCP server and external APIs, design mobile and wearable companion apps, and implement drone control interfaces.Add life logging and journaling features, voice biomarker analysis for health monitoring, privacy modes and local‑only processing capabilities. | Each experimental feature should be implemented as a plug‑in with clearly defined APIs.Register plug‑ins with the orchestrator so they can be invoked on demand.Ensure heavy computation runs asynchronously or offloads to dedicated processes.Coordinate with UI developer for new visualizations and with memory developer for analytics. | Develop on `advanced-features` branch. Prioritize features based on user requirements.Maintain separate feature toggles (via config) so experimental features can be enabled/disabled.Document integration steps for each plug‑in.
Enhancements & New Features Developer | Implement enhancement backlog: tool & workflow integration, knowledge base ingestion and retrieval, natural conversation (endpoint detection, noise suppression, backchanneling), call transcription and analysis, agent squads & flow blocks with multi‑LLM support, telephony & cross‑device sync (including offline mode), emotional & multi‑party interactions, privacy controls & human oversight, real‑time translation with voice cloning. | You are an AI coding assistant responsible for integrating new enhancements into ARCHER.Implement connectors to external tools (CRM, schedulers, Google Drive), build document ingestion pipeline with OCR and vector databases, implement advanced voice detection (endpoint detection, noise suppression, backchanneling), integrate real‑time call transcription and analysis, design squad-based agent coordination and flow blocks with multi‑model support, implement telephony (SIP/WebRTC) and cross‑device synchronization with offline capabilities, add emotional and multi-party interaction support, implement configurable privacy controls and human-in-the-loop oversight, and build real-time translation and voice cloning. | Develop enhancements as modular services or plug‑ins with clear APIs; register them with orchestrator; coordinate with memory and voice modules.Store ingested knowledge in vector databases and expose retrieval APIs.Implement call transcription services that feed summary back into memory.Ensure privacy controls are configurable; integrate translation pipeline into voice module. | Work on `enhancements` branch. Provide regular updates and clearly note any dependencies on other modules.Coordinate with all other developers when adding features that cross module boundaries.Prioritize features based on project goals and maintain test coverage.
Security & Privacy Developer | Design and implement security and privacy framework: multi-layer authentication, failsafe/kill-switch, session management, audit trail, privacy modes and data minimization. | You are an AI coding assistant responsible for ARCHER’s security and privacy framework.Implement multi-layer security features such as local-first execution, voice authentication with auto-reset, kill-switch commands, verifier independence (separate AI verifying critical actions), privacy schedules, data redaction and user consent flows.Design audit logging for all sensitive actions and memory access.Work within `src/agents/authority_manager.py`, `src/config/security.yaml` and other relevant files. | Integrate security checks into orchestrator and automation modules via decorators or middleware.Expose functions for the voice and UI modules to query and adjust privacy modes.Ensure logs are stored securely and accessible for auditing; integrate with memory without storing raw sensitive data. | Work on `security-privacy` branch. Collaborate with all developers to enforce security patterns.Run threat modelling and privacy impact assessments for new features.Review code contributions for compliance with security policies.

## Dev Agents Plan Detailed
Agent Name | Role & Scope | Dependencies & Setup | Code Skeleton & File Names | Execution & Logging Instructions | Communication & QC | Repo & Inventory | Enhanced Guidelines & Testing
Voice Interaction Developer (Agent_V) | Implement voice pipeline: wake-word detection, speaker verification, STT, TTS, voice cloning, emotion detection, multi-language support, streaming and filler audio. | - Install libraries: `pip install openwakeword faster-whisper speechbrain f5-tts pydub numpy`- Additional: `pip install torchaudio` if GPU is available for voice models.- Place requirements in `requirements_voice.txt` and run `pip install -r requirements_voice.txt` on first run. | Create `src/voice/pipeline.py` with the following skeleton:```pythonimport pyaudioimport numpy as npclass VoicePipeline: def __init__(self, stt_model=None, tts_model=None): self.stt_model = stt_model self.tts_model = tts_model def listen_and_transcribe(self): """Capture audio, run VAD, return transcription via faster-whisper""" return "" def synthesize_speech(self, text, voice="default"): """Generate speech using f5-tts or other provider""" return b"" def authenticate_voice(self, audio_chunk, user_profile): """Verify speaker identity using speechbrain speaker verification""" return False def detect_emotion(self, audio_chunk): """Detect emotions from speech (e.g., happy/sad)""" return "neutral"``` | 1. Checkout branch `agent_voice` or create a worktree for isolated development.2. Install dependencies via `pip`.3. Copy the skeleton to `src/voice/pipeline.py`. If a file already exists, integrate the skeleton by adding missing methods and comment on modifications.4. Study the project’s README and Project Plan sheet to understand how the voice pipeline interacts with the orchestrator and UI.5. Implement STT using `faster-whisper` with streaming; implement TTS using `f5-tts`; integrate wake‑word detection using `openwakeword`; add voice authentication with `speechbrain` speaker verification; implement emotion detection via acoustic features. For multi-language support, ensure STT/TTS select models based on detected language.6. Keep a detailed log in `logs/agent_voice_log.md` noting install commands, files added/modified, issues encountered and decisions made.7. Once the core functions are operational, write unit tests under `tests/voice/` (optional) to validate them.8. Mark completion in `QC_Checklist.md` and proceed to audit another module as described in the QC process. | - Communicate with other agents by appending messages to `agent_messages.md`. Prefix each message with `From: Agent_V To: <target_agent> Date:` and describe the question or information clearly.- After finishing your module, open `QC_Checklist.md` and mark the voice component as **Complete**. Then choose any other component marked *Complete* and perform a code review (read the module, verify adherence to integration guidelines, run tests). Without modifying that module, write pass/fail status and notes in the same row.- If you encounter conflicts with the overall architecture or need coordination (e.g., interface mismatch), document the issue in your log and in `agent_messages.md` addressed to the Dev Orchestrator (Agent_COORD). Wait for guidance before proceeding. | Clone repo, inspect src/voice (tts.py, stt.py, wake_word.py); test existing F5-TTS using test scripts. TEST COMMANDS: - python test_tts.py - python test_f5tts_simple.py - python simple_tts_test.py DOCUMENT in logs/agent_voice_inventory.md: - All existing files in src/voice/ - What works (F5-TTS playback, Windows audio) - What's missing (wake word, voice auth, STT, multi-language, filler audio, barge-in) INTEGRATION PLAN: ENHANCE existing F5-TTS in tts.py, DO NOT rebuild. Read existing F5TTSService class and extend it. | EXTEND EXISTING F5-TTS: - Multi-language support (langdetect + model selection) - Filler audio system (pre-recorded pondering sounds) - Barge-in handling (VAD + immediate TTS kill) - Emotion detection (pitch/energy/spectral features) ADD NEW FEATURES: - Wake word detection: openWakeWord - Voice authentication: speechbrain speaker verification - STT: Faster-Whisper with GPU acceleration MEMORY INTEGRATION (MANDATORY): ```python from src.memory.long_term import VectorMemory from src.memory.episodic import EpisodicMemory class VoicePipeline: def __init__(self): self.memory = VectorMemory(collection_name="agent_v") self.episodic = EpisodicMemory() def handle(self, query: str): # Store interactions self.episodic.log(agent="agent_v", event="query", data={"text": query}) ``` WINDOWS REQUIREMENTS: - Audio: sounddevice (playback), pyaudio (recording) - Paths: from pathlib import Path - Virtual env: venv\Scripts\activate - GPU: Verify torch.cuda.is_available() ERROR HANDLING: ```python import logging logger = logging.getLogger(__name__) def synthesize_speech(self, text): try: return self.tts_engine.synthesize(text) except Exception as e: logger.exception(f"TTS error: {e}") return self.fallback_tts(text) ``` TESTING: - Unit: pytest tests/voice/test_voice_pipeline.py -v - Integration: Test with orchestrator - Performance: wake_word <200ms, STT <800ms, TTS <1s - Windows: Verify on Windows 11 COMPLETION: - [ ] F5-TTS still works - [ ] All new features implemented - [ ] Memory integration complete - [ ] All tests passing - [ ] QC_Checklist.md updated
UI & Visualization Developer (Agent_UI) | Design the desktop and cross‑platform UIs: orb animation, webcam feed, 3D/AR avatar, multi‑monitor support, and gradio web interface. | - Install UI libraries: `pip install PyQt5 opencv-python gradio` for desktop and web interfaces.- For 3D/AR features, install `pip install pythreejs pyopengl`.- Add these to `requirements_ui.txt`. | Create `src/ui/main.py` with:```pythonimport sysfrom PyQt5.QtWidgets import QApplication, QWidgetclass ArcherUI(QWidget): def __init__(self): super().__init__() self.init_ui() def init_ui(self): self.setWindowTitle("ARCHER") # TODO: add orb, webcam feed, 3D avatar widgets self.show()def run_ui(): app = QApplication(sys.argv) ui = ArcherUI() sys.exit(app.exec_())if __name__ == "__main__": run_ui()```Create additional files in `src/ui/components/` for orb animation, webcam display (using OpenCV), 3D avatar rendering, and AR overlay. | 1. Work on branch `agent_ui`. Install the UI dependencies using pip.2. Examine existing UI code in the repository (e.g., gradio interface). Integrate the skeleton above if no file exists or extend current code by adding new classes for orb animation, video feed and AR.3. Follow the Project Plan to ensure your UI exposes controls for voice activation, shows context/history, and supports multi‑monitor layouts.4. Keep notes of all changes in `logs/agent_ui_log.md`, including design decisions, third‑party assets, and issues.5. Provide at least one example layout file in `layouts/` demonstrating how the UI will arrange components.6. After implementation, mark UI module as complete in `QC_Checklist.md` and review another module following the QC procedure. | - Use `agent_messages.md` to request or share interface specifications (e.g., what methods the voice pipeline will expose to the UI). Prefix messages appropriately.- Update `QC_Checklist.md` when finishing your module and after performing a review of another module. Provide pass/fail notes.- If you need additional assets (images, icons), list them in your log and note that they should be added by a human later. | Clone repo, review src/ui and UI files in root directory. EXISTING UI FILES (test ALL): - archer_gui.py (Gradio interface) - desktop_gui.py (PyQt) - working_desktop_gui.py (PyQt) - working_tts_gui.py (PyQt) - integrated_desktop_gui.py (PyQt) - simple_desktop_gui.py (PyQt) TEST EACH: - python archer_gui.py - python working_tts_gui.py - python desktop_gui.py DOCUMENT in logs/agent_ui_inventory.md: - Which UIs launch successfully - Features each has (orb? webcam? voice integration?) - Which to use as primary enhancement target INTEGRATION PLAN: Choose best working UI and enhance it. DO NOT delete existing UIs. | ENHANCE EXISTING UI: - Orb animations (5 states: idle, listening, thinking, speaking, error) - Webcam integration (coordinate with Agent_ENV) - Canvas widgets (charts, images, PDFs, web content) - Multi-monitor support (PyQt screen detection) - Accessibility features (keyboard nav, screen reader, high contrast) - Error display and user feedback MEMORY INTEGRATION (MANDATORY): ```python from src.memory.long_term import VectorMemory from src.memory.episodic import EpisodicMemory class ArcherUI: def __init__(self): self.memory = VectorMemory(collection_name="agent_ui") self.episodic = EpisodicMemory() ``` WINDOWS REQUIREMENTS: - Desktop: PyQt5 or PyQt6 - Web: Gradio (already working) - Paths: Use pathlib.Path - Multi-monitor: QApplication.screens() ERROR HANDLING: ```python def update_display(self, content): try: self.canvas.render(content) except Exception as e: logger.exception(f"Render error: {e}") self.show_error_notification(str(e)) ``` INTEGRATION: - Voice pipeline: Bi-directional events - Orchestrator: WebSocket or REST API - Vision: Webcam feed display TESTING: - All existing UIs still launch - Orb animations smooth - Webcam displays correctly - Windows compatibility verified COMPLETION: - [ ] Existing UIs work - [ ] New features added - [ ] Memory integration complete - [ ] Tests passing
Orchestration & Memory Developer (Agent_ORCH) | Develop the central orchestrator that routes user requests to sub‑agents, coordinates multi‑agent interactions, manages reasoning chains and conversation context, and implements memory (short‑term, long‑term, semantic, episodic) storage. | - Install libraries: `pip install fastapi uvicorn langchain chromadb faiss-cpu networkx`.- For memory persistence, optionally install `pip install sqlite-utils` or use built‑in JSON storage.- Add these to `requirements_orch.txt`. | Create `src/agents/orchestrator.py` with:```pythonclass Orchestrator: def __init__(self): self.agents = {} self.memory = None # placeholder for memory manager def register_agent(self, name, agent_interface): self.agents[name] = agent_interface def handle_request(self, request): """Route requests based on intent and maintain conversation context.""" # TODO: implement routing and context management return None```Create `src/memory/base_memory.py` with a `MemoryStore` class for short‑term and long‑term memory and methods `add()` and `retrieve()`. | 1. Create branch `agent_orch` and install dependencies.2. Study the project structure to understand existing agents and how they are called. Expand the orchestrator skeleton with functions to parse user intents, register agents, maintain conversation histories, and call the correct agent.3. Design the memory store: implement short‑term memory for recent conversation, long‑term memory with vector embeddings using `chromadb` or `faiss`, and semantic/episodic retrieval functions.4. Document API contracts: define Python methods (or HTTP endpoints using FastAPI) that other modules will call to register and query the orchestrator.5. Keep detailed log in `logs/agent_orch_log.md` summarizing design decisions, memory schema, and any conflicts.6. Upon completion, update `QC_Checklist.md` and review at least one other module. | - Use `agent_messages.md` to announce new API interfaces or changes so other developers can align their modules.- In the QC checklist, ensure the orchestrator passes integration tests (i.e., can successfully call at least one other agent). Note any issues.- If memory integration or agent registration conflicts arise, record them in your log and ask the Dev Orchestrator (Agent_COORD) via `agent_messages.md` for guidance. | Clone repo, read src/agents/orchestrator.py COMPLETELY. EXISTING CODE: - orchestrator.py EXISTS - contains working orchestrator - 9 specialized agents EXIST: assistant.py, therapist.py, trainer.py, stock_expert.py, authority_manager.py, evidence_processor.py, federated_learning.py, governance.py, proactive.py TEST EXISTING: ```python from src.agents.orchestrator import Orchestrator orch = Orchestrator() # Verify initialization works ``` DOCUMENT in logs/agent_orch_inventory.md: - Current orchestrator capabilities - How agents are registered now - Routing logic that exists - What's MISSING vs. spreadsheet specs INTEGRATION PLAN: ENHANCE existing orchestrator, keep it working. All 9 agents must continue functioning. | ENHANCE EXISTING ORCHESTRATOR: - Agent registration API (standardized) - Intent classification (rule-based + LLM) - Memory enhancement patterns - Multi-agent squads (health, productivity, finance) - Quality gate verification - Performance monitoring - Error recovery and fallbacks BUILD 4-TIER MEMORY SYSTEM (YOUR RESPONSIBILITY): ```python from src.memory.long_term import VectorMemory # ChromaDB from src.memory.episodic import EpisodicMemory # SQLite from src.memory.semantic import SemanticMemory # Knowledge graph class Orchestrator: def __init__(self): # Global memories self.long_term = VectorMemory(collection_name="global") self.episodic = EpisodicMemory() self.semantic = SemanticMemory() # Agent registry self.agents = {} def register_agent(self, name, agent_instance): self.agents[name] = agent_instance def handle_request(self, query, context=None): # 1. Retrieve memories memories = self.long_term.search(query, limit=5) recent = self.episodic.get_recent(limit=10) # 2. Classify intent intent = self.classify_intent(query) # 3. Route to agent agent = self.select_agent(intent) response = agent.handle(query, {"memories": memories, "recent": recent}) # 4. Quality gate if not self.verify_quality(response): return self.fallback_response(query) # 5. Store self.episodic.log(event="response", data={"query": query, "response": response}) return response ``` WINDOWS REQUIREMENTS: - Paths: pathlib.Path - Database: SQLite (built-in) - Vector DB: ChromaDB (Windows compatible) TESTING: - Existing orchestrator still works - All 9 agents still callable - New routing logic correct - Memory system stores/retrieves - Performance: routing <500ms, memory <200ms COMPLETION: - [ ] Existing orchestrator enhanced - [ ] 9 agents still work - [ ] 4-tier memory complete - [ ] All tests passing
Environmental Interaction Developer (Agent_ENV) | Implement computer-vision features: passive observation, pose estimation, gaze and head tracking, gesture recognition, activity recognition, object detection, and face recognition. | - Install dependencies: `pip install opencv-python mediapipe face-recognition torch torchvision numpy`.- Additional: `pip install pillow` for image processing.- Add to `requirements_env.txt`. | Create `src/vision/vision_agent.py`:```pythonimport cv2import mediapipe as mpclass VisionAgent: def __init__(self): self.pose = mp.solutions.pose.Pose() self.hands = mp.solutions.hands.Hands() def process_frame(self, frame): """Process a video frame and return detected poses, gestures, objects.""" # TODO: implement detections using mediapipe and opencv return {}``` | 1. Work in branch `agent_env`. Install dependencies.2. Build an application within `vision_agent.py` that captures frames from the webcam, processes them to detect poses, hands, faces, and objects, and outputs structured data.3. Integrate the detection outputs with the orchestrator via a callback or message (e.g., call `orchestrator.handle_event('gesture', data)` for recognized gestures).4. Document tuning parameters (e.g., confidence thresholds) in your log file `logs/agent_env_log.md`.5. After completion, update `QC_Checklist.md` and review another module. Do not modify other modules during review. | - Use `agent_messages.md` to coordinate with the UI and orchestrator developers regarding how vision events should trigger UI updates or actions.- In your QC reviews, verify that the vision module does not lock camera resources when not in use and that it gracefully handles missing cameras.- Report any hardware limitations or performance issues in your log and to Agent_COORD. | Clone repo, inspect src/vision (observer.py, emotion_detection.py, activity_recognition.py). CHECK FOR: - Existing vision modules - Current capabilities - Camera integration approach TEST if vision code exists: ```python # Try importing existing modules from src.vision.observer import Observer ``` DOCUMENT in logs/agent_env_inventory.md: - Files found in src/vision/ - Existing capabilities (emotion detection? activity recognition?) - What's missing (passive observation, pose estimation, gesture recognition, gaze tracking) INTEGRATION PLAN: Build on existing code, add missing features. Ensure Windows camera compatibility. | IMPLEMENT ENVIRONMENTAL PERCEPTION: - Passive observation (continuous monitoring) - Pose estimation (MediaPipe Pose) - Gesture recognition (MediaPipe Hands) - Activity classification (custom model) - Gaze detection (eye tracking) - Object tracking - Face recognition (with consent) MEMORY INTEGRATION (MANDATORY): ```python from src.memory.episodic import EpisodicMemory class VisionAgent: def __init__(self): self.episodic = EpisodicMemory() def process_frame(self, frame): # Detect pose, gestures, etc. results = self.detect(frame) # Log events (NOT raw video) if results['gesture']: self.episodic.log( agent="agent_env", event="gesture_detected", data={"gesture": results['gesture'], "confidence": results['confidence']} ) ``` WINDOWS CAMERA: - OpenCV with Windows camera indices - Network cameras: RTSP streams (Blue Iris) - Release resources: cv2.VideoCapture.release() PRIVACY CONTROLS (CRITICAL): ```python class PrivacyManager: def is_vision_allowed(self, feature): # Check user settings return feature not in self.disabled_features ``` ERROR HANDLING: ```python def capture_frame(self): try: ret, frame = self.camera.read() if not ret: raise CameraError("Failed to capture") return frame except Exception as e: logger.exception(f"Camera error: {e}") return None ``` TESTING: - Camera access on Windows - Pose estimation accuracy - Privacy controls work - No resource leaks COMPLETION: - [ ] All features implemented - [ ] Privacy controls working - [ ] Tests passing
Automation & System Control Developer (Agent_AUTO) | Develop automation for computer control: window management, remote access, macro recording and playback, system-level triggers and file management. | - Install libraries: `pip install pyautogui psutil keyboard paramiko`.- Additional: `pip install pynput` for low-level keyboard/mouse hooks.- Add to `requirements_auto.txt`. | Create `src/automation/controller.py`:```pythonimport pyautoguiimport subprocessclass AutomationController: def open_application(self, path): subprocess.Popen([path]) def click(self, x, y): pyautogui.click(x, y) def type_text(self, text): pyautogui.write(text)```Create `src/automation/remote.py` for remote connections (e.g., via paramiko). | 1. Create branch `agent_auto` and install dependencies.2. Expand `controller.py` to include functions for scrolling, keystrokes, multi-monitor window management, and macro recording/playback.3. Implement remote control capabilities in `remote.py` using SSH (paramiko) or RDP. Ensure that security credentials are read from secure storage (coordinate with Enhancements developer for encryption).4. Keep `logs/agent_auto_log.md` detailing OS-specific challenges, security considerations, and command triggers.5. After completion, update the QC checklist and audit another module without making changes. | - Use `agent_messages.md` to coordinate with the Security developer about safe handling of credentials and with the Orchestrator developer to define events (e.g., `orchestrator.trigger('open_app', {'path': path})`).- When reviewing other modules, ensure that no insecure macros or commands are present. | Clone repo, inspect src/automation if present and related scripts. EXISTING FILES: - archer_windows.bat - setup_windows_archer.py - Check for src/automation/ directory DOCUMENT in logs/agent_auto_inventory.md: - Existing automation scripts - Windows-specific functionality - What automation exists vs. needed INTEGRATION PLAN: Windows-native implementation. Build on existing scripts, add new automation features. | IMPLEMENT AUTOMATION: - High-level command API for orchestrator - Window management (pyautogui, pywin32) - Macro recording/playback - Remote access (secure) - Smart-home integration (Home Assistant MCP) - File management MEMORY INTEGRATION: ```python from src.memory.episodic import EpisodicMemory class AutomationController: def __init__(self): self.episodic = EpisodicMemory() def execute_command(self, command): # Log ALL automation actions self.episodic.log( agent="agent_auto", event="command_executed", data={"command": command, "timestamp": datetime.now()} ) ``` WINDOWS REQUIREMENTS: - Window control: pyautogui or pywin32 - Subprocess: shell=True for .bat files - Paths: pathlib.Path SECURITY: ```python def execute_command(self, command): # Require confirmation for destructive ops if self.is_destructive(command): if not self.request_permission(command): return {"success": False, "error": "Permission denied"} try: result = self.run(command) return {"success": True, "result": result} except Exception as e: logger.exception(f"Command error: {e}") return {"success": False, "error": str(e)} ``` TESTING: - Window management works - Macros don't interfere - HALT command immediate - All security checks pass COMPLETION: - [ ] All features implemented - [ ] Security verified - [ ] Tests passing
Specialized Agents Developer (Agent_SPEC) | Implement proactive and domain-specific agents: therapist, trainer, financial expert, R&D agent, education coach, productivity coach, social manager, creative collaborator and security/privacy agent. | - Install LLM libraries: `pip install openai anthropic tiktoken` (choose whichever is permitted), and retrieval libraries like `pip install chromadb`.- For scheduling or finance tasks, install `pip install pandas yfinance`.- Create `requirements_spec.txt`. | Create `src/agents/specialized/therapist.py`, `trainer.py`, etc., each with a class containing a `handle(query, context)` method that uses an LLM to generate appropriate responses. Example skeleton:```pythonclass TherapistAgent: def handle(self, query, context): # TODO: call LLM API with system prompt tuned for therapy return "I'm here to listen."```Create an `__init__.py` that registers these agents for discovery. | 1. Work in branch `agent_spec`. Install dependencies.2. Define a base class for specialized agents to ensure consistency (e.g., `class BaseSpecializedAgent`). Each specific agent should implement a `handle()` method and be registered with the orchestrator via a plugin registration.3. For each agent, create system prompts and sample personas. Document them in your log file `logs/agent_spec_log.md`.4. Ensure that sensitive or regulated domains (therapy, finance) include human‑in‑the‑loop safeguards; note any ethical considerations.5. After building, update `QC_Checklist.md` and review another module. | - Use `agent_messages.md` to coordinate with Orchestrator and Enhancements developers on how specialized agents are invoked (e.g., via voice commands or UI selection).- When reviewing other modules, ensure that the orchestrator correctly delegates to specialized agents and that their outputs are handled. | Clone repo, inspect src/agents for existing specialized agents. 9 AGENTS ALREADY EXIST: - assistant.py - therapist.py - trainer.py - stock_expert.py - authority_manager.py - evidence_processor.py - federated_learning.py - governance.py - proactive.py READ EACH AGENT: - Understand current APIs - Document capabilities - Note integration patterns DOCUMENT in logs/agent_spec_inventory.md: - Each existing agent's functionality - Their current APIs and endpoints - Which new agents need creation - How existing agents integrate with orchestrator INTEGRATION PLAN: ENHANCE existing 9 agents, create new ones following same pattern. DO NOT rebuild existing agents. | IMPLEMENT/ENHANCE SPECIALIZED AGENTS: EXISTING AGENTS (ENHANCE): - assistant.py - Add more tool integrations - therapist.py - Enhance behavioral monitoring - trainer.py - Integrate with Agent_ENV for pose analysis - stock_expert.py - Add real-time market APIs - authority_manager.py - Coordinate with Agent_SEC - evidence_processor.py - Coordinate with Agent_ENV - federated_learning.py, governance.py, proactive.py - Document and enhance NEW AGENTS (CREATE): - R&D Agent - Learning Coach - Productivity Coach - Social Relationship Manager - Creative Collaborator BASE PATTERN FOR ALL AGENTS: ```python from src.memory.long_term import VectorMemory from src.memory.episodic import EpisodicMemory class BaseSpecializedAgent: def __init__(self, name: str): self.name = name self.memory = VectorMemory(collection_name=f"agent_{name}") self.episodic = EpisodicMemory() def handle(self, query: str, context: dict): # Retrieve relevant memories memories = self.memory.search(query, limit=5) # Process with domain knowledge response = self.process(query, memories, context) # Store interaction self.memory.add(text=f"Q: {query}\nA: {response}") self.episodic.log(agent=self.name, event="interaction", data={"query": query}) return response ``` REGISTRATION: ```python # Each agent registers with orchestrator orchestrator.register_agent('therapist', TherapistAgent()) ``` TESTING: - All 9 existing agents still work - New agents integrate with orchestrator - Memory integration complete COMPLETION: - [ ] Existing agents enhanced - [ ] New agents created - [ ] All registered - [ ] Tests passing
Advanced & Experimental Features Developer (Agent_ADV) | Develop advanced capabilities: visual question answering, screen content understanding, document extraction (OCR and layout analysis), predictive assistance, personal analytics/life logging, voice biomarkers, privacy modes, and mobile/IoT clients. | - Install deep-learning and OCR libraries: `pip install transformers sentencepiece torchvision pytesseract beautifulsoup4 requests`.- For biomarker analysis or speaker health metrics, install `pip install librosa torchaudio`.- For document layout analysis, install `pip install pdfplumber`.- Record these in `requirements_adv.txt`. | Create `src/advanced/advanced_features.py` with skeleton methods:```pythonclass AdvancedFeatures: def visual_qa(self, image_path, question): """Use a VQA model (e.g., OFA or LLaVA) to answer questions about images""" return "" def extract_text(self, image_path): """Extract and structure text from documents using pytesseract and layout models""" return "" def predict_context(self, context_history): """Implement predictive assistance based on conversation history""" return ""```Also plan for modules like `life_logging.py` and `mobile_client.py`. | 1. Work in branch `agent_adv`. Install required libraries.2. Implement VQA using a pre-trained model (e.g., LLaVA via HuggingFace). For document extraction, use OCR (pytesseract) and optionally layout analysis (like LayoutLM).3. Design predictive assistance functions that analyze memory/history to anticipate user needs; propose suggestions.4. Work with Orchestrator and UI teams to expose these features via appropriate commands.5. Keep `logs/agent_adv_log.md` with detailed experiments, model choices, and performance notes.6. Mark completion in QC checklist and review another module. | - Announce any heavy model downloads or system requirements in `agent_messages.md` so other developers know about compute needs.- In QC, verify that advanced features gracefully degrade when resources are limited (e.g., fallback to offline OCR). | Clone repo, inspect for existing advanced or enhancements modules. CHECK: - src/advanced/ directory - Any experimental features - Plug-in architecture if exists DOCUMENT in logs/agent_adv_inventory.md: - Existing advanced features - Current plug-in system if any - Integration with orchestrator INTEGRATION PLAN: Plug-in style implementation. Each feature separate, can be enabled/disabled. | IMPLEMENT ADVANCED FEATURES (PLUG-IN ARCHITECTURE): - Visual Q&A (LLaVA or similar VQA model) - Screen content understanding (OCR + layout analysis) - Document extraction (PyPDF, pytesseract) - Predictive assistance (ML on user patterns) - Personal analytics dashboard - Life logging (journaling system) - Voice biomarkers (health monitoring) - Privacy modes (local-only processing) PLUG-IN PATTERN: ```python class AdvancedFeature: def __init__(self, feature_name: str, enabled: bool = True): self.name = feature_name self.enabled = enabled def execute(self, *args, **kwargs): if not self.enabled: return {"error": "Feature disabled"} return self.process(*args, **kwargs) # Register with orchestrator orchestrator.register_plugin('visual_qa', VisualQAFeature()) ``` MEMORY INTEGRATION: ```python from src.memory.long_term import VectorMemory class AdvancedFeatures: def __init__(self): self.memory = VectorMemory(collection_name="agent_adv") ``` WINDOWS REQUIREMENTS: - Screen capture: pyautogui or Windows API - GPU acceleration: torch.cuda for heavy models - Local processing: Respect privacy modes TESTING: - Each feature works independently - Plug-in enable/disable works - GPU utilized correctly - Privacy modes functional COMPLETION: - [ ] All features implemented - [ ] Plug-in architecture working - [ ] Tests passing
Enhancements & Integration Developer (Agent_ENH) | Implement feature enhancements and integration backlog: tool/workflow integrations, knowledge-base ingestion and RAG, natural conversation (endpoint detection, noise suppression, backchanneling), call transcription and analysis, agent squads and flow blocks, telephony integration, cross-device synchronization with offline mode, emotional & multi-party interaction, privacy controls, human oversight, and real-time translation with voice cloning. | - Install additional libraries: `pip install chromadb langdetect textblob assemblyai` for knowledge base and transcription; `pip install rnnoise` or `deepfilternet` for noise suppression; `pip install pyaudio` for audio streaming; `pip install twilio` for telephony; `pip install deep-translator` or `googletrans==4.0.0rc1` for translation; `pip install elevenlabs` for voice cloning; `pip install openai` for RAG and chat; `pip install ttsmodels` for additional voices.- Provide a `requirements_enh.txt` file. | Create `src/enhancements/integration_agent.py` with:```pythonclass IntegrationAgent: def integrate_tool(self, tool_name, *args, **kwargs): """Register and invoke external tools via plugin system.""" return None def ingest_documents(self, paths): """Ingest documents into vector store for RAG""" return None def detect_end_of_speech(self, audio_stream): """Endpoint detection using VAD""" return True def suppress_noise(self, audio_chunk): """Apply noise suppression (RNNoise/DeepFilterNet)""" return audio_chunk```Add other modules: `call_transcription.py` using AssemblyAI or Whisper; `multi_language_translation.py` using translation API and voice cloning; `privacy_manager.py` for privacy settings. | 1. Work on branch `agent_enh`. Install the wide range of dependencies.2. Implement ingestion of user documents into a vector database (chromadb) with embedding generation; design retrieval functions for RAG.3. Build a plugin system for tool integrations; define a registry of external tools (calendar, email, file management) and example connectors.4. Implement endpoint detection using voice activity detection (VAD); integrate noise suppression using RNNoise/DeepFilterNet; design backchanneling behaviours for natural conversation.5. Implement call recording and transcription using AssemblyAI or a local Whisper model; include diarization and summarisation; ensure privacy compliance.6. Add telephony integration via Twilio or Vapi to handle inbound/outbound calls; plan cross-device sync (synchronising session state across devices) and offline mode using on-device models.7. Build real‑time translation with voice cloning: detect language, translate text, synthesise speech using cloned voice. Document languages supported.8. Integrate privacy controls and human oversight; design settings for data sharing, anonymisation, and manual confirmation for sensitive actions.9. Log all activities and decisions in `logs/agent_enh_log.md` and mark progress in the QC checklist. | - Coordinate heavily with all other agents: share changes via `agent_messages.md` when new tools or APIs are introduced; ask Orchestrator developer how to expose these enhancements.- When performing QC on other modules, ensure their interfaces can accommodate enhancements like endpoint detection and noise suppression.- Document any limitations or API keys required in your log; do not commit secrets. | Clone repo, inspect for existing enhancements and integration modules. CHECK: - src/enhancements/ directory - Any RAG or knowledge base code - Agent coordination systems DOCUMENT in logs/agent_enh_log.md: - Current enhancement features - Integration patterns - Cross-agent dependencies INTEGRATION PLAN: Modular services. Heavy coordination with ALL other agents required. | IMPLEMENT ENHANCEMENTS (MODULAR SERVICES): KNOWLEDGE BASE & RAG: ```python from sentence_transformers import SentenceTransformer import chromadb class KnowledgeBaseRAG: def __init__(self): self.client = chromadb.PersistentClient(path="data/memory/knowledge_base") self.collection = self.client.get_or_create_collection("knowledge_base") self.embedder = SentenceTransformer('all-MiniLM-L6-v2') def ingest_documents(self, paths: List[Path]): # Extract text from PDFs, docs, etc. # Create embeddings # Store in vector DB pass def retrieve(self, query: str, limit: int = 3): # Retrieve relevant chunks for RAG pass ``` NATURAL CONVERSATION: ```python import webrtcvad class ConversationEnhancements: def __init__(self): self.vad = webrtcvad.Vad(mode=3) def detect_endpoint(self, audio_chunk): # VAD for end-of-speech detection pass def suppress_noise(self, audio): # Noise suppression using noisereduce pass def should_backchannel(self, context): # Determine if backchanneling appropriate pass ``` AGENT SQUADS: ```python class AgentSquad: def __init__(self, name: str, agents: List[str]): self.name = name self.agents = agents def execute(self, query: str, orchestrator): # Coordinate multiple agents for complex task pass ``` CALL TRANSCRIPTION: ```python from faster_whisper import WhisperModel class CallTranscriptionService: def transcribe_call(self, audio_path): # Transcribe with diarization pass def analyze_call(self, transcript): # Extract action items, sentiment pass ``` REAL-TIME TRANSLATION: ```python from deep_translator import GoogleTranslator from langdetect import detect class TranslationService: def translate_with_voice(self, audio, target_lang, tts_service, stt_service): # STT → Translate → TTS with voice cloning pass ``` WINDOWS REQUIREMENTS: - Noise suppression: noisereduce (Windows compatible) - Telephony: Twilio SDK - Offline mode: Local models only TESTING: - RAG with documents - Endpoint detection with voice pipeline - Agent squads coordination - All integrations work COMPLETION: - [ ] All enhancements implemented - [ ] Integration complete - [ ] Tests passing
Development Orchestrator & QC Agent (Agent_COORD) | Coordinate all CLI agents, maintain the project plan and QC checklist, schedule integration, perform final quality control and resolve conflicts. | - No special libraries required beyond `pip install pytest pandas` for running tests and reading logs.- Optionally, install `pip install coverage` for code coverage analysis. | Create `orchestrator_dev.py` (outside `src/` as a management script):```pythonimport subprocessfrom pathlib import Pathclass DevOrchestrator: def __init__(self, repo_path: Path): self.repo_path = repo_path def run_tests(self): subprocess.run(['pytest', '-q'], cwd=self.repo_path) def read_qc_checklist(self): # TODO: parse QC_Checklist.md to see component statuses pass def integrate_branches(self): # TODO: merge feature branches into main after QC pass``` | 1. Assume the role of a project manager. Familiarize yourself with the `ARCHER Core Features` and `Project Plan` sheets and ensure each agent understands how their component fits into the whole.2. Create `QC_Checklist.md` in the repository root with a table listing all components (Voice, UI, Orchestration, Env, Automation, Specialized Agents, Advanced Features, Enhancements), columns for Assigned Agent, Status, Reviewer, Review Result, and Notes.3. Monitor `agent_messages.md` and individual `logs/*.md` files to track progress and identify blockers. Provide clarifications or instructions by writing into `agent_messages.md` with clear recipient information.4. Schedule integration checkpoints: at these times, merge completed branches into a staging branch, run tests using `pytest`, and document results in `integration_log.md`.5. Perform quality control: review each component’s code, run unit tests, and verify integration. Update the QC checklist status (Pass/Fail) with reasons.6. If conflicts arise (e.g., API changes), work with the relevant agent by writing explicit tasks into `agent_messages.md`. Summarize the resolution in your log.7. At the end of development cycle, integrate all components into the main branch and summarise the development in `integration_log.md`. | - You are the central point of coordination. Use `agent_messages.md` to assign tasks, clarify requirements, and resolve disagreements. Prefix messages with `From: Agent_COORD To: <agent>`.- Keep `QC_Checklist.md` and `integration_log.md` up to date. Ensure every module is reviewed by at least one peer agent and by you.- Remind agents about limited context windows: encourage them to record important context or assumptions in their logs so future agents understand decisions. | Clone repo, review entire codebase structure. VERIFY: - agent_messages.md exists - QC_Checklist.md exists - logs/ directory structure - All 9 branches exist (voice-pipeline, ui, orchestrator, vision, automation, specialized-agents, advanced-features, enhancements, main) CREATE: - logs/agent_coord_log.md - Initial coordination message in agent_messages.md INTEGRATION PLAN: Coordinate all agents, manage QC, schedule integration, run tests. | COORDINATION RESPONSIBILITIES: SETUP INFRASTRUCTURE: 1. Verify agent_messages.md exists 2. Verify QC_Checklist.md exists 3. Verify logs/ directory structure 4. Verify all 9 branches exist POST KICKOFF: ```markdown From: Agent_COORD To: ALL_AGENTS Date: [DATE] Subject: Development Kickoff Status: Infrastructure ready. All branches created. CRITICAL REMINDERS: - F5-TTS is WORKING - enhance it, don't rebuild! - Orchestrator exists - enhance it, don't rebuild! - 9 specialized agents exist - enhance them, don't rebuild! - Windows-native required - use Windows tools and paths - 4-tier memory MANDATORY for all agents Development Order: 1. Agent_ORCH (establishes patterns) 2. Agent_V & Agent_UI (parallel) 3. Agent_SPEC & Agent_ENV (parallel) 4. Agent_AUTO 5. Agent_ENH & Agent_ADV (parallel) Coordinate via agent_messages.md Update QC_Checklist.md as you complete ``` MONITOR PROGRESS: ```python import subprocess def run_tests(): result = subprocess.run(['pytest', 'tests/', '-v'], capture_output=True) return result.returncode == 0 def check_integration(): # Verify all agents can be imported # Test orchestrator routing # Verify memory system works pass ``` QUALITY GATES: - All agents pass unit tests - Integration tests pass - Performance benchmarks met - Peer reviews complete - Documentation complete MERGE PROTOCOL: 1. Agent marks complete in QC_Checklist.md 2. Peer review performed 3. Agent_COORD runs integration tests 4. Merge to main if all pass COMPLETION: - [ ] All agents deployed - [ ] All tests passing - [ ] Integration complete

## Cross-Agent Guidelines
Category | Summary
Repository State Awareness | All agents MUST: 1. Clone repository first: git clone https://github.com/JaxArcher/ARCHER_WINDOWS.git 2. Switch to their branch: git checkout [branch-name] 3. Review ALL existing code in their assigned area 4. Test existing functionality using provided test scripts 5. Document findings in logs/agent_[id]_inventory.md 6. Create integration plan: ENHANCE existing code, do NOT rebuild from scratch CRITICAL: F5-TTS is WORKING, Orchestrator EXISTS, 9 Specialized Agents EXIST - these must continue functioning after your changes!
Windows-Specific Requirements | WINDOWS-NATIVE PROJECT - All code must work on Windows 11: FILE PATHS: ```python from pathlib import Path root = Path("D:/ARCHER_WINDOWS") # ✅ Correct # NOT: root = "/home/user/ARCHER" # ❌ Linux path ``` AUDIO LIBRARIES: ```python import sounddevice as sd # ✅ Windows playback import pyaudio # ✅ Windows recording (requires binary) # NOT: import alsaaudio # ❌ Linux only ``` VIRTUAL ENVIRONMENT: ```powershell venv\Scripts\activate # ✅ Windows # NOT: source venv/bin/activate # ❌ Linux ``` GPU VERIFICATION: ```python import torch assert torch.cuda.is_available(), "CUDA required!" print(f"Using: {torch.cuda.get_device_name(0)}") ```
Existing Multi-Agent System | ORCHESTRATOR & AGENTS ALREADY EXIST: ORCHESTRATOR: src/agents/orchestrator.py - READ IT COMPLETELY before making changes - Understand current routing logic - Keep it working while adding features 9 SPECIALIZED AGENTS EXIST: 1. assistant.py 2. therapist.py 3. trainer.py 4. stock_expert.py 5. authority_manager.py 6. evidence_processor.py 7. federated_learning.py 8. governance.py 9. proactive.py YOUR JOB: ENHANCE these agents, do NOT rebuild them! Test before coding: ```python from src.agents.orchestrator import Orchestrator orch = Orchestrator() # Should initialize without errors ```
4-Tier Memory Integration | ALL AGENTS MUST USE 4-TIER MEMORY SYSTEM: TIER 1: Short-term (LLM context window) TIER 2: Long-term (VectorMemory with ChromaDB) TIER 3: Episodic (EpisodicMemory with SQLite) TIER 4: Semantic (Knowledge graph) STANDARD INTEGRATION PATTERN: ```python from src.memory.long_term import VectorMemory from src.memory.episodic import EpisodicMemory class YourAgent: def __init__(self, agent_id: str): # Each agent gets own collection self.memory = VectorMemory(collection_name=f"agent_{agent_id}") self.episodic = EpisodicMemory() def handle(self, query: str, context: dict = None): # 1. Retrieve memories memories = self.memory.search(query, limit=5) recent = self.episodic.get_recent(agent=self.agent_id, limit=10) # 2. Process with memories response = self.process(query, memories, recent, context) # 3. Store new memories self.memory.add( text=f"Q: {query}\nA: {response}", metadata={"agent": self.agent_id, "timestamp": datetime.now().isoformat()} ) self.episodic.log( agent=self.agent_id, event_type="interaction", data={"query": query, "response": response} ) return response ``` MEMORY APIS (defined by Agent_ORCH): - VectorMemory.search(query, limit) → List[str] - VectorMemory.add(text, metadata) → None - EpisodicMemory.log(agent, event_type, data) → None - EpisodicMemory.get_recent(agent, limit) → List[dict]
F5-TTS Integration Context | F5-TTS IS WORKING - DO NOT REBUILD IT! LOCATION: src/voice/tts.py CLASS: F5TTSService EXISTING METHODS: - synthesize(text, voice_profile) → audio - synthesize_streaming(text) → generator - clone_voice(audio_sample) → voice_profile - set_emotion(emotion_type) → None WORKING FEATURES: - Text-to-speech synthesis - Voice cloning from samples - Emotional control - Windows audio playback YOUR JOB (Agent_V): ADD these features to existing F5-TTS: - Multi-language support (detect language, select model) - Filler audio (pre-recorded pondering sounds) - Barge-in handling (VAD + immediate kill) - Streaming improvements ALSO ADD (separate from F5-TTS): - Wake word detection (openWakeWord) - Voice authentication (speechbrain) - STT (Faster-Whisper) TEST EXISTING FIRST: ```python python test_tts.py python test_f5tts_simple.py ``` INTEGRATION PLAN: 1. Read tts.py completely 2. Understand F5TTSService class 3. Extend the class with new features 4. Keep all existing methods working 5. Add new methods alongside existing ones
Testing & Validation | ALL AGENTS MUST IMPLEMENT COMPREHENSIVE TESTING: UNIT TESTS: ```python # tests/agents/test_[agent_name].py import pytest from src.agents.[your_agent] import YourAgent class TestYourAgent: @pytest.fixture def agent(self): return YourAgent() def test_initialization(self, agent): assert agent is not None assert hasattr(agent, 'handle') def test_basic_query(self, agent): response = agent.handle("test query", {}) assert response is not None def test_memory_integration(self, agent): agent.handle("remember this", {}) memories = agent.memory.search("remember") assert len(memories) > 0 ``` INTEGRATION TESTS: ```python # tests/integration/test_[agent]_integration.py def test_orchestrator_communication(orchestrator, your_agent): orchestrator.register_agent('your_name', your_agent) response = orchestrator.handle_request("test") assert response is not None ``` PERFORMANCE TESTS: ```python import time def test_response_latency(agent): start = time.time() response = agent.handle("benchmark query") latency = time.time() - start assert latency < YOUR_TARGET_LATENCY ``` RUN TESTS: ```bash # Unit tests pytest tests/agents/test_[agent].py -v # Integration tests pytest tests/integration/ -v # All tests pytest tests/ -v --cov=src ``` VALIDATION CHECKLIST: - [ ] All unit tests passing - [ ] Integration tests passing - [ ] Performance benchmarks met - [ ] Windows compatibility verified - [ ] Memory integration working - [ ] Error handling tested - [ ] Documentation complete
Error Handling & Recovery | ALL AGENTS MUST IMPLEMENT ROBUST ERROR HANDLING: EXCEPTION HIERARCHY: ```python class AgentError(Exception): """Base exception for agent errors.""" pass class InitializationError(AgentError): """Agent failed to initialize.""" pass class ProcessingError(AgentError): """Error during request processing.""" pass class MemoryError(AgentError): """Error accessing memory system.""" pass ``` STANDARD PATTERN: ```python import logging from typing import Optional, Dict, Any logger = logging.getLogger(__name__) class YourAgent: def handle(self, query: str, context: Dict = None) -> Optional[Dict[str, Any]]: """Handle request with comprehensive error handling.""" # Validate input if not query or not isinstance(query, str): logger.warning(f"{self.name}: Invalid query") return { 'success': False, 'error': 'Invalid query format', 'error_type': 'validation_error' } try: # Main processing result = self.process(query, context) return { 'success': True, 'result': result, 'agent': self.name } except ProcessingError as e: logger.error(f"{self.name} processing error: {e}") return { 'success': False, 'error': 'Processing failed', 'error_type': 'processing_error', 'fallback': self.get_fallback_response(query) } except MemoryError as e: logger.error(f"{self.name} memory error: {e}") # Continue without memory if necessary return self.process_without_memory(query, context) except Exception as e: logger.exception(f"{self.name} unexpected error: {e}") return { 'success': False, 'error': 'Internal error occurred', 'error_type': 'unexpected_error', 'fallback': self.get_safe_fallback(query) } ``` FALLBACK STRATEGIES: ```python def get_fallback_response(self, query: str) -> str: """Multi-level fallback strategy.""" # Level 1: Try simplified processing try: return self.simple_process(query) except Exception: pass # Level 2: Rule-based response try: return self.rule_based_response(query) except Exception: pass # Level 3: Template response return f"I encountered an issue processing your request. Please try rephrasing." ``` LOGGING LEVELS: - DEBUG: Detailed diagnostic info - INFO: General operation info - WARNING: Unexpected but handled - ERROR: Error that affected operation - CRITICAL: System-wide failure ERROR NOTIFICATION: ```python def notify_error(self, error: Exception, context: dict): """Notify orchestrator of critical errors.""" self.episodic.log( agent=self.name, event_type="error", data={ "error": str(error), "error_type": type(error).__name__, "context": context, "timestamp": datetime.now().isoformat() } ) ```
Automation & CI/CD | AUTOMATED VALIDATION & CONTINUOUS INTEGRATION: PRE-COMMIT HOOKS: Create .git/hooks/pre-commit: ```bash #!/bin/bash # Run before each commit # Code style python -m flake8 src/ --max-line-length=120 # Type checking python -m mypy src/ --ignore-missing-imports # Tests python -m pytest tests/ -v # Check for secrets git diff --cached --name-only ¦ xargs grep -l "sk-" && echo "Possible API key found!" && exit 1 exit 0 ``` GITHUB ACTIONS WORKFLOW: Create .github/workflows/ci.yml: ```yaml name: ARCHER CI on: [push, pull_request] jobs: test: runs-on: windows-latest steps: - uses: actions/checkout@v2 - name: Set up Python uses: actions/setup-python@v2 with: python-version: '3.11' - name: Install dependencies run: ¦ python -m pip install --upgrade pip pip install -r requirements.txt pip install pytest flake8 mypy - name: Lint with flake8 run: flake8 src/ --max-line-length=120 - name: Type check with mypy run: mypy src/ --ignore-missing-imports - name: Run tests run: pytest tests/ -v --cov=src - name: Check Windows compatibility run: python scripts/verify_windows_compatibility.py ``` CONTINUOUS TESTING SCRIPT: ```python # tests/run_all_tests.py import subprocess import sys def run_tests(): """Run all test suites.""" test_suites = [ ("Unit Tests", "pytest tests/agents/ -v"), ("Integration Tests", "pytest tests/integration/ -v"), ("Performance Tests", "pytest tests/performance/ -v"), ] all_passed = True for name, command in test_suites: print(f"\n{'='*60}") print(f"Running: {name}") print('='*60) result = subprocess.run(command.split(), capture_output=True) if result.returncode != 0: print(f"❌ {name} FAILED") all_passed = False else: print(f"✅ {name} PASSED") return 0 if all_passed else 1 if __name__ == "__main__": sys.exit(run_tests()) ``` AUTOMATED VALIDATION: ```python # quality_gate.py def check_quality_gates(component: str) -> bool: """Verify component passes all quality gates.""" gates = { 'code_style': check_code_style(component), 'type_hints': check_type_hints(component), 'docstrings': check_docstrings(component), 'tests': run_tests(component), 'coverage': check_coverage(component, min_coverage=80), 'windows_compat': check_windows_compatibility(component) } all_passed = all(gates.values()) # Log results for gate, passed in gates.items(): status = "✅" if passed else "❌" print(f"{status} {gate}: {'PASS' if passed else 'FAIL'}") return all_passed ```
Integration Protocols | STANDARD INTER-AGENT COMMUNICATION: AGENT MESSAGE FORMAT: ```python from dataclasses import dataclass from datetime import datetime from typing import Any, Dict, Optional @dataclass class AgentMessage: from_agent: str to_agent: str message_type: str # 'request', 'response', 'notification', 'error' content: Dict[str, Any] timestamp: datetime = datetime.now() correlation_id: Optional[str] = None ``` COMMUNICATION METHODS: 1. VIA ORCHESTRATOR (Recommended): ```python class YourAgent: def send_to_agent(self, target_agent: str, message: dict): return self.orchestrator.route_message( AgentMessage( from_agent=self.name, to_agent=target_agent, message_type='request', content=message ) ) ``` 2. MESSAGE QUEUE (For async): ```python import zmq class AgentMessageBus: def __init__(self): self.context = zmq.Context() self.publisher = self.context.socket(zmq.PUB) self.publisher.bind("tcp://127.0.0.1:5555") def publish(self, topic: str, message: AgentMessage): self.publisher.send_string(f"{topic} {message.to_json()}") ``` 3. SHARED MEMORY (For coordination): ```python class SharedContext: def __init__(self): self.state = {} self.lock = threading.Lock() def update(self, key: str, value: Any): with self.lock: self.state[key] = value def get(self, key: str) -> Any: with self.lock: return self.state.get(key) ``` MEMORY ACCESS PROTOCOL: READ ACCESS: ```python # Each agent can search global memories global_memories = orchestrator.long_term.search(query, limit=5) # And their own agent-specific memories my_memories = self.memory.search(query, limit=5) ``` WRITE ACCESS: ```python # Store in agent-specific collection self.memory.add( text="important information", metadata={"agent": self.name, "category": "user_preference"} ) # Store in shared/global (coordinate with orchestrator) orchestrator.store_global_memory( text="system-wide information", metadata={"source": self.name} ) ``` AGENT REGISTRATION: ```python class Orchestrator: def register_agent(self, name: str, agent_instance, capabilities: List[str]): self.agents[name] = { 'instance': agent_instance, 'capabilities': capabilities, 'subscriptions': [] # Topics agent subscribes to } ``` SUBSCRIPTION MODEL: ```python # Agent declares interests class YourAgent: def __init__(self): self.subscriptions = [ 'user_query', 'system_event', f'agent_{self.name}_direct' ] def on_message(self, message: AgentMessage): if message.message_type == 'request': return self.handle(message.content) ```